## Sheet1
Tasks |  | Who`s handling |  | Status | Priority
| Scrum Master | Product Owner | Developers | Comments | 1-5
Implement SysData | Firas | Saleh | saleh |  | 5
Implementing read write, update methods of JSON file | Firas | Saleh | Saleh |  | 4 | מקרא צבעים
Implement Game ,Queen | Firas | Saleh | Firas |  | 5
Implement the following classes:Board, Location, Piece, Soldier | Firas | Saleh | Aseel |  | 5
Implementation of Tile,YellowTile, BlueTile | Firas | Saleh | Saleh |  | 4 |  | בטיפול
Implement fields,getters,setters for Player and Turn Class | Firas | Saleh | Maryam |  | 5 |  | לא באיטרציה הנוכחית
Implementation of the Question class - writing attributes, getters and setters | Firas | Saleh | Aseel |  | 5
Implementation of the Answer class Writing attributes of getters and setters | Firas | Saleh | Maryam |  | 5